## Summary
data-store — implementation changes
Java 17 · Spring 7 (no Boot) · Jackson 3 · Fory · Chronicle Map 3 API · Ignite 2.18 · 2026-10-19
Metric | Value | Source
Functional requirements | 41 | Functional Requirements
met | 40 | Functional Requirements, Status
met, still to verify on real libraries | 4 | Functional Requirements, Status
implemented, not tested here | 1 | Functional Requirements, Status
Changes logged | 53 | Change Log
of which implemented as planned | 52 | Change Log, Status
of which changed from plan | 1 | Change Log, Status
YAML keys documented | 24 | YAML Reference
allowed in dataset-defaults | 7 | YAML Reference
Store settings documented | 25 | Store Settings
Ignite dataset-level settings | 14 | Store Settings
Classes in data-store-core | 19 | Packages & Classes
Packages in data-store-core | 8 | Hardcoded: root, annotation, config, lookup, spi, store, spring, internal
Test cases (unique) | 30 | Tests
Test executions passed | 96 | Tests (contract runs on 4 stores)
Test executions failed | 0 | Tests
Open items | 5 | Decisions & Open Items
Sheets
Functional Requirements |  | Every requirement from the design discussion with acceptance criteria, implementation, linked changes and verifying tests
Change Log |  | Every change implemented: before, after, reason, files, status
YAML Reference |  | Every common configuration key, level, default, and whether dataset-defaults may set it
Store Settings |  | Chronicle / Ignite / memory settings, store vs dataset level
Packages & Classes |  | Module → package → class map with role and visibility
Tests |  | Test inventory and results per store
Decisions & Open Items |  | Agreed decisions, open verification items and accepted risks
Verification note |  | Results are from compiling and running against hand-written stand-ins for Spring, Jackson, Fory, Chronicle Map, Ignite and JUnit (Maven Central was unreachable). Confirm with ./gradlew build against the real libraries.

## Functional Requirements
Req ID | Category | Requirement | Source | Acceptance criteria | Implementation | Linked changes | Verifying tests | Status
FR-01 | Pipeline | Multiple atomic batch jobs hand data to each other through a shared store instead of files | Initial requirement | A job's output dataset is readable by the next job in another JVM using the same configuration | DataStore + Dao per dataset; namespace + partition shared via one YAML | C001, C008, C009 | secondStoreInSameJvmSeesTheSameData; wholePipelineOnTheMemoryStore | Met (cross-JVM to verify on real Chronicle/Ignite)
FR-02 | Pipeline | Behave like JVMs sharing memory: jobs in separate JVMs read and write the same data | Clarified: 'mimic JVMs sharing memory' | Chronicle: same files mapped by every JVM on a host; Ignite: same caches from every host | ChronicleStore (memory-mapped files, no server); IgniteStore (thin client) | C008, C009 | Chronicle/Ignite contract tests | Met (cross-JVM to verify on real libraries)
FR-03 | Pipeline | Daily flow: load reference data, load primary data, parallel processing jobs, derived outputs, flattened CSV export; next day starts fresh | Daily lifecycle described | Each step marks its output COMPLETE; next partition is independent of the previous one | Manifest, createAll, partition per day, sample Pipeline steps | C014, C047, C053 | wholePipelineOnTheMemoryStore; partitionsAreIsolatedAndKeptUntilDestroyed | Met
FR-04 | Pipeline | Downstream jobs start only when upstream data is complete | Hand-off between jobs | requireComplete fails with the list of datasets not COMPLETE; require-complete blocks lookups into incomplete datasets | Manifest.requireComplete; require-complete setting | C047, C020 | manifestTracksCompletion | Met
FR-05 | Pipeline | Export rebuilds a flat CSV from nested objects | Daily lifecycle described | One row per nested line with parent fields repeated; deterministic order | Sample Pipeline.export over EMBEDDED snapshot | C045, C053 | wholePipelineOnTheMemoryStore | Met (sample)
FR-06 | Stores | Whole operation uses either Chronicle or Ignite, never mixed | 'One whole goal is either Chronicle or Ignite' | One store-type per configuration; per-dataset store choice not possible | store-type at whole-store level | C012, C013 | validationErrors | Met
FR-07 | Stores | Chronicle for one large host (128 cores, 3 TB), no service to run | Single big machine scenario | No server process; data off-heap in mapped files; parallel splits | ChronicleStore with splits, FileLocks | C008, C049 | Chronicle contract tests | Met (stand-in verified)
FR-08 | Stores | Ignite 2 for multi-host pipelines via thin client | 'Use Ignite 2 instead of 3' | Caches per dataset per partition; bulk getAll; partition-aware scans | IgniteStore | C009, C025, C033 | Ignite contract tests | Met (needs live cluster test)
FR-09 | Stores | Plain Java map (memory) store for unit tests and local runs, in core | Memory store as default in core | No extra module; default store-type; behaves like real stores (copies on read) | MemoryStore | C007 | Memory contract tests; Core tests | Met
FR-10 | Stores | Any custom store works by implementing Store | 'Just implement Store - it should work' | Selected by class name or ServiceLoader; gets own typed settings; passes contract | Store + StoreMap SPI | C010, C011 | CountingStore contract tests; customStoreReceivesItsSettings | Met
FR-11 | Library | Three modules published separately to Artifactory: core, chronicle, ignite | Module split requested | Each module publishes its own jar; consumer adds core + one store | Gradle multi-project with maven-publish | C001 | Gradle dry run | Met
FR-12 | Library | Teams use central DAOs; they do not implement data access | 'DAOs centralized across' | Dao obtained from DataStore.dao(...) for any configured dataset | Dao, DataStore | C003 | All contract tests | Met
FR-13 | Library | Plain Spring only (no Spring Boot); also usable without Spring | 'Avoid Spring Boot - only Spring' | @Import(DataStoreConfiguration.class); DataStore.builder() without Spring | DataStoreConfiguration, DataStore.Builder | C002, C051 | Core tests (no Spring) | Met
FR-14 | Library | Flink/Spark executors run Spring for the job's lifetime | Consumer types described | One context per executor JVM shared by tasks; Flink release hook | ExecutorContext | C050 | - | Implemented (not tested here)
FR-15 | Library | Limit number of classes; organise in subpackages | 'Limit classes, create multiple subpackages' | 19 classes in core across 8 packages; 1 class per store module | Package layout | C004, C005, C006 | - | Met
FR-16 | Library | Java 17, Spring 7, Jackson 3, Chronicle Map 3, Ignite 2, Fory latest | Tech stack requested | Versions pinned in libs.versions.toml | gradle/libs.versions.toml | C001, C009 | - | Met (versions to confirm in Artifactory)
FR-17 | Domain | Domain classes live in team-owned libraries; consumer YAML lists datasets and domain classes | Domains are separate libs | Library has no domain code; datasets bound by class name from YAML | DatasetConfig.value / key / id | C034 | All contract tests | Met
FR-18 | Domain | Existing domain classes keep working for older apps | 'Old apps continue with existing way' | Full-object fields stay; REFERENCE mode never modifies caller objects | into fields + strip copy | C044, C046 | referenceModeStoresOnlyIdsAndLeavesCallerObjectsAlone | Met
FR-19 | Domain | Relations by annotation or YAML (no wrapper type) | 'Can Lookup be an annotation?' | @Lookup on field, or lookups: in YAML; both validated; conflict fails | @Lookup, LookupConfig | C034, C035, C036 | validationErrors; eagerReadResolvesTheFullGraph | Met
FR-20 | Domain | Id from annotation or YAML; composite key from several fields | 'Are @Id/@Lookup mandatory?' | @Id, id: field, or id: [f1, f2] with key: | DataStore.Builder.meta() | C030 | keyBuiltFromSeveralFields | Met
FR-21 | Keys | Custom key classes always supported (immutable, equals/hashCode) | 'Custom key support is always required' | Records or final classes with simple fields; deterministic in every JVM; enums supported | KeyCodec; Chronicle byte keys; Ignite BinaryObject keys | C029, C031, C032, C033 | compositeRecordKeyWithEnum; keyBuiltFromSeveralFields | Met
FR-22 | Lookups | Nested object holds the id of another dataset's object (lazy-fetch style); works on Chronicle and Ignite | Lazy-fetch requirement | Only ids stored in REFERENCE mode; resolved from the target dataset | Lookup links, LookupResolver | C037, C044 | eagerReadResolvesTheFullGraph (all stores) | Met
FR-23 | Lookups | No per-item network calls at 10M volume | 'Is lazy fetch over network a killer?' | One bulk call per target dataset per level per page | LookupResolver level loop; Dao pages/findAllById | C040, C043 | eagerPageIsOneBulkCallPerDatasetPerLevel | Met
FR-24 | Lookups | Resolve policy per lookup: EAGER or LAZY, with dataset and default levels | Resolve policy requested | lookup → dataset → dataset-defaults → LAZY; per-call override | lookup-resolve-policy, Resolve | C017, C020, C038 | perCallOverrides; eagerReadResolvesTheFullGraph | Met
FR-25 | Lookups | EAGER or resolve() resolves the full graph to any depth | 'System should do all n depth' | Targets' own lookups resolved regardless of their policy; cycles terminate | LookupResolver full-depth loop | C039, C041 | eagerReadResolvesTheFullGraph; cyclesTerminateAndReusePageObjects | Met
FR-26 | Lookups | Datasets define only direct members; target dataset's mapping drives the next level | Clarified expectation | Each dataset lists only its own lookups; chain followed through targets | buildLinks per dataset | C037 | eagerReadResolvesTheFullGraph | Met
FR-27 | Lookups | One utility to resolve all lookups at once or on need | 'Provide 1 util class for LookupResolver' | resolve(page), resolve(page, names...), scope(page) lazy | LookupResolver, LookupResult | C042 | resolverOnDemandAndScope | Met
FR-28 | Lookups | Same id referenced by several objects is fetched once and shared | 'Cached centrally on JVM side?' | Within a page: one fetch and one instance; across pages: local-cache | Per-call identity map; local-cache | C041, C028 | resolverOnDemandAndScope | Met
FR-29 | Lookups | Missing lookup target behaviour configurable | Rename to on-missing-target | FAIL (default) or NULL, set on the target dataset | on-missing-target | C018 | missingTargetFailsByDefault; missingTargetIsNullWhenConfigured; datasetOverridesDatasetDefaults | Met
FR-30 | Storage | Option to store the complete object with member domains | 'Store complete object ... at dataset/store level' | storage-mode EMBEDDED at dataset or dataset-defaults; cycles supported | EMBEDDED mode with reference tracking | C045 | embeddedModeStoresTheWholeGraph | Met
FR-31 | Cache | Local JVM short-circuit for repeated lookups, no Spring Cache, no Caffeine, unlimited | local-cache requirements | local-cache: true caches encoded values in an unbounded ConcurrentHashMap per dataset per JVM | Dao local cache | C027, C028 | Contract tests (region local-cache) | Met
FR-32 | Config | YAML or JSON, one common root, store-type selects the backend | Config layout requested | Both formats load; store-type: memory ¦ chronicle ¦ ignite ¦ class | DataStoreConfig.parse | C012, C013 | jsonConfigWorksToo | Met
FR-33 | Config | dataset-defaults overridable at dataset level, field by field | 'dataset-defaults can be override at dataset level' | Unset dataset fields inherit; store blocks merge per field; effective settings logged | DatasetConfig.over(), mergeBlocks | C020, C021, C023 | datasetOverridesDatasetDefaults; datasetDefaultsAreValidated | Met
FR-34 | Config | Ignite configurable per dataset; Chronicle kept as it is | Store config per dataset | Ignite cache settings at dataset level; connection at store level | IgniteStore.DatasetSettings | C025, C026 | Ignite contract tests | Met
FR-35 | Config | Store-specific validation | 'Specific validation of YAML' | Active store blocks strictly validated; typos fail with full path | storeBlock() + typed settings classes | C022 | validationErrors; typoInYamlIsRejectedAtStartup | Met
FR-36 | Config | Namespace isolates teams sharing a machine or cluster | Teams on same machine | Different namespaces never see or delete each other's data | Namespace in paths / cache names | C014 | partitionsAreIsolatedAndKeptUntilDestroyed | Met
FR-37 | Config | Partition key built from custom parts (${A}_${B}) | 'Say partition - custom concatenated key' | partition.parts joined with '_'; placeholders resolved | DataStore.Builder.partition() | C014, C024 | jsonConfigWorksToo | Met
FR-38 | Lifecycle | Rerun yesterday (any partition) when required | 'Can I run the job for yesterday?' | Start with another partition value; data of other partitions untouched | Partition per run; reset(dataset) | C014, C048 | partitionsAreIsolatedAndKeptUntilDestroyed; overwriteDeleteAndReset | Met
FR-39 | Lifecycle | Retention unlimited by default; delete manually; never delete in-use data | Retention requirements | No automatic deletion; destroyPartition refuses own/in-use partition | destroyPartition, FileLocks | C015, C048, C049 | partitionsAreIsolatedAndKeptUntilDestroyed | Met (Ignite: no cross-host lock)
FR-40 | Quality | Fail fast at startup on any configuration or mapping error | Validation expectations | Store, blocks, classes, ids, keys, lookup targets and types validated before jobs run | DataStore.Builder.start() | C021, C022 | validationErrors; datasetDefaultsAreValidated | Met
FR-41 | Quality | Sample Spring consumer app and JUnit examples on the memory store | Sample requested | Production YAML runs on memory in a unit test | samples/sample-app, PipelineTest | C053 | wholePipelineOnTheMemoryStore | Met

## Change Log
ID | Area | Module | Change | Before | After / implemented | Why / requested | Main files | Status
C001 | Architecture | all | Three published library modules plus samples | Single design discussion, no code | data-store-core, data-store-chronicle, data-store-ignite (published to Artifactory); samples/sample-domain and samples/sample-app (not published) | Requested: separate modules, one library teams import | settings.gradle.kts, build.gradle.kts | Implemented
C002 | Architecture | core | No Spring Boot; plain Spring 7 only | Boot auto-configuration in early design | @Import(DataStoreConfiguration.class) with @PropertySource; no Boot dependency | Requested: avoid Spring Boot | spring/DataStoreConfiguration.java | Implemented
C003 | Architecture | core | Spring Data repositories and Spring Cache dropped | CrudRepository + Spring Cache in early design | Own generic Dao<T,K> obtained from DataStore.dao(...) | Spring Data hid remote calls (N+1) and needed overriding for bulk; Spring Cache not needed | Dao.java, DataStore.java | Implemented
C004 | Architecture | core | Core split into subpackages, class count kept low | All core classes in one package | Root (DataStore, Dao, Manifest, DataStoreException) + annotation, config, lookup, spi, store, spring, internal; 19 classes in core, 1 per store module | Requested: limit classes, multiple subpackages | data-store-core/src/main/java/com/acme/datastore/** | Implemented
C005 | Architecture | core | Internal model made public in .internal package | Package-private Model in root package | internal.Model public (needed across packages), Javadoc marks it as not API | Consequence of subpackages | internal/Model.java | Implemented
C006 | Architecture | core | Resolver decoupled through Backend interface | Resolver called DataStore internals directly | LookupResolver.Backend (meta, datasetOf, fetch, requireComplete) implemented by DataStore | Keeps lookup package independent of DataStore internals | lookup/LookupResolver.java, DataStore.java | Implemented
C007 | Stores | core | Memory store built into core and the default | Separate in-memory provider | store-type: memory is the default; ConcurrentHashMap per dataset per partition; copies on read (values stored as bytes) | Requested: memory store in core for JUnit/examples | store/MemoryStore.java | Implemented
C008 | Stores | chronicle | Chronicle Map store with splits | n/a | One Chronicle map file per split under <base-dir>/<namespace>/<partition>/<dataset>/; byte[] keys and values; split by stable hash of encoded key; split count fixed at create and read back | Single big machine use case; no server needed | chronicle/ChronicleStore.java | Implemented
C009 | Stores | ignite | Ignite 2 thin client store (replaces Ignite 3) | Ignite 3 tables in an earlier build | One PARTITIONED/ATOMIC cache per dataset per partition (<ns>__<dataset>__<partition>); values as Fory bytes; composite keys as BinaryObject; scan splits group Ignite partitions | Requested: use Ignite 2 instead of 3 | ignite/IgniteStore.java | Implemented
C010 | Stores | core | Custom store = implement Store + StoreMap | Provider SPI with more types | Store (name, settingsType, datasetSettingsType, init, open, partitions, destroy, lock) + StoreMap (bytes in/out); selected by name via ServiceLoader or by class name | Requested: any custom store just implements Store | spi/Store.java, spi/StoreMap.java, test CountingStore.java | Implemented
C011 | Stores | core | Stores only see bytes | Stores handled serialization | Core encodes values (Fory) and handles storage modes and lookups; stores store byte[] | Makes custom stores simple; local-cache can cache bytes safely | spi/StoreMap.java, internal/Model.java | Implemented
C012 | Config | core | One common root 'datastore' for YAML or JSON | Separate root per backend (earlier plan) | Single datastore block; JSON accepted (read by the YAML parser) | Requested: common YAML, JSON if needed | config/DataStoreConfig.java | Implemented
C013 | Config | core | store -> store-type | store: | store-type: memory ¦ chronicle ¦ ignite ¦ <class name> | Requested rename | config/DataStoreConfig.java, DataStore.Builder.storeType() | Implemented
C014 | Config | core | run-date -> partition with named parts | run-date: ${RUN_DATE} | partition.parts joined with '_' in order (e.g. NA_20261018) | Requested: custom concatenated partition key | DataStore.java (partition()) | Implemented
C015 | Config | core | Retention removed (unlimited by default) | retention-days: 2 | Nothing deleted automatically; destroyPartition(p) for explicit deletes; manual directory delete for Chronicle | Requested: keep everything unless deleted manually | DataStore.destroyPartition | Implemented
C016 | Config | core | lookup-defaults split into lookup-resolver + dataset-defaults | lookup-defaults (resolve, missing, parallelism, require-complete...) | lookup-resolver: parallelism, page-size, max-depth, single-read-warn (whole store); per-dataset parts moved to dataset-defaults | Each setting has exactly one home | config/DataStoreConfig.java | Implemented
C017 | Config | core | resolve -> lookup-resolve-policy | resolve: | lookup-resolve-policy: EAGER ¦ LAZY (dataset-defaults, dataset, lookup entry) | Requested rename | config/DataStoreConfig.java | Implemented
C018 | Config | core | missing -> on-missing-target | missing: | on-missing-target: FAIL ¦ NULL, read from the TARGET dataset | Requested rename | config/DataStoreConfig.java, lookup/LookupResolver.java | Implemented
C019 | Config | core | resolver -> lookup-resolver | (proposed) resolver: | lookup-resolver: | Requested rename | config/DataStoreConfig.java | Implemented
C020 | Config | core | dataset-defaults with field-by-field override | Each dataset repeated all settings | dataset-defaults holds any dataset setting; dataset overrides per field; nested store blocks merge per field | Requested | DataStoreConfig.DatasetConfig.over(), mergeBlocks() | Implemented
C021 | Config | core | dataset-defaults restricted to shared settings | n/a | value, key, id and lookups rejected in dataset-defaults at startup | They belong to one dataset | DataStore.Builder.start() | Implemented
C022 | Config | core | Strict validation of the active store's blocks only | Unknown keys failed regardless | Active store's blocks bound strictly; blocks of other installed stores ignored; unknown names fail (e.g. datasets.country.splitz) | Switch store-type with one line | DataStore.Builder.storeBlock() | Implemented
C023 | Config | core | Effective settings logged per dataset | n/a | Startup log lists id source, storage-mode, policy, on-missing-target, require-complete, local-cache, splits and merged store block | Make inheritance visible | DataStore.Builder.start() | Implemented
C024 | Config | core | Placeholders | n/a | ${NAME} / ${NAME:default} from system properties then env, or Spring Environment | Partition and store-type from environment | DataStore.Builder.resolvePlaceholders | Implemented
C025 | Config | ignite | Ignite cache settings per dataset | backups, data-region, default-splits at store level | Store level: addresses, partition-awareness, timeout-millis. Dataset level (and dataset-defaults.ignite): cache-mode, atomicity-mode, backups, data-region, group-name, read-from-backup, write-synchronization-mode, partition-loss-policy, rebalance-mode, rebalance-batch-size, copy-on-read, statistics-enabled, affinity-field, ignite-cache-partitions | Requested: all possible config at dataset level | ignite/IgniteStore.java | Implemented
C026 | Config | chronicle | Chronicle settings kept as they were | n/a | Store level: base-dir, default-splits, headroom, segments-per-split. Dataset level: entries, avg-value-bytes, avg-key-bytes (can now also be set in dataset-defaults.chronicle) | Requested: keep Chronicle as is | chronicle/ChronicleStore.java | Implemented
C027 | Cache | core | Caffeine dropped | Caffeine local cache with max size | No Caffeine dependency | Requested | build files, Dao.java | Implemented
C028 | Cache | core | local-cache is an unbounded ConcurrentHashMap | local-cache: { enabled, max-entries } | local-cache: true ¦ false; caches encoded bytes per dataset per JVM; no cap, no eviction | Requested: drop cap, keep unlimited | Dao.java | Implemented
C029 | Keys | core | Custom keys always supported | Long/Integer/String only | Simple types or records / final classes with final simple fields and equals/hashCode; deterministic KeyCodec | Requested: custom key classes | spi/KeyCodec.java | Implemented
C030 | Keys | core | Composite key from several fields in YAML | n/a | id: [tradeId, legNo] with key: <class> | Existing classes without a key object | DataStore.Builder.meta() | Implemented
C031 | Keys | chronicle | Split by stable hash of encoded key | Split by key.hashCode() | Hash of KeyCodec bytes (enum hashCode differs between JVMs) | Correctness across JVMs | chronicle/ChronicleStore.java | Implemented
C032 | Keys | chronicle | Key layout change detected | n/a | key-fingerprint stored per dataset; opening with a changed key class fails with a clear message | Avoid silent corruption | chronicle/ChronicleStore.java | Implemented
C033 | Keys | ignite | Portable key components | n/a | Enums -> name, LocalDate/LocalTime -> long, LocalDateTime/Instant/BigInteger -> String inside BinaryObject keys | Ignite binary keys must be portable and deterministic | ignite/IgniteStore.java | Implemented
C034 | Domain | core | @Id and @Lookup optional; YAML equivalent | Lookup<T> wrapper type | Annotations or YAML (id:, lookups:); domain libs need core only as compileOnly, or nothing with YAML | Requested: annotations instead of wrapper, existing domain libs | annotation/*.java | Implemented
C035 | Domain | core | @Lookup(resolve=) -> @Lookup(resolvePolicy=) | resolve attribute | resolvePolicy attribute (same meaning as YAML lookup-resolve-policy) | Consistent naming | annotation/Lookup.java | Implemented
C036 | Domain | core | Lookup<T> wrapper removed | Lookup<T> field type | Plain id fields (single or collection) with @Lookup or YAML | One approach only | annotation/Lookup.java | Implemented
C037 | Lookups | core | Datasets declare only direct members; target drives the next level | n/a | Each dataset lists its own lookups; the target dataset's own lookups are used for the next level | Requested | DataStore.Builder.buildLinks() | Implemented
C038 | Lookups | core | EAGER / LAZY resolve policy | n/a | EAGER fills into fields on every DAO read; LAZY on request via LookupResolver; per-call override Resolve.EAGER / LAZY | Requested: resolve policy per lookup | Dao.java, lookup/LookupResolver.java | Implemented
C039 | Lookups | core | Full-depth resolution | Depth-limited in an earlier plan | Whatever is resolved is resolved to any depth; max-depth optional (0 = unlimited) | Requested: eager or resolve means all n depth | lookup/LookupResolver.java | Implemented
C040 | Lookups | core | Bulk per level | n/a | One getAll per target dataset per level, datasets of a level in parallel; verified by call-counting test | Avoid N+1 at 10M scale | lookup/LookupResolver.java | Implemented
C041 | Lookups | core | Cycles terminate and reuse objects | n/a | Per-call identity map; page objects reused when a lookup points back at them | Customer -> primaryOrder -> Order cycles | lookup/LookupResolver.java | Implemented
C042 | Lookups | core | LookupResolver utility | n/a | resolve(page) (all), resolve(page, names...), scope(page) (lazy, page-wide on first get), resolve(one) | Requested: resolve all in one go or on need | lookup/LookupResolver.java, lookup/LookupResult.java | Implemented
C043 | Lookups | core | Single findById warning | n/a | Warn once per dataset after single-read-warn single reads resolving EAGER lookups | Guard against N+1 loops | Dao.java | Implemented
C044 | Storage modes | core | REFERENCE mode | n/a | Only ids stored; into fields left out of a copy (caller object untouched); id filled from into object if empty; mismatch fails | Older apps keep full objects; data-store apps store keys | internal/Model.java | Implemented
C045 | Storage modes | core | EMBEDDED mode | n/a | Whole object graph stored; Fory reference tracking for cycles; only empty into fields resolved | Requested: option to store complete objects | internal/Model.java, DataStore.java | Implemented
C046 | Storage modes | core | REFERENCE implemented as path copy, not field skipping | Plan: codec skips into fields | Copies only objects along paths that hold into fields, nulls them in the copy, encodes the copy | Fory per-dataset field skipping could not be confirmed | internal/Model.java | Implemented (changed from plan)
C047 | Lifecycle | core | Manifest as commit point | n/a | CREATED / LOADING / COMPLETE / FAILED per dataset per partition with record count; requireComplete(...) | Hand-off between jobs | Manifest.java | Implemented
C048 | Lifecycle | core | createAll / reset / destroyPartition | n/a | createAll idempotent; reset clears one dataset; destroyPartition refuses own partition and in-use partitions (Chronicle file lock) | Reruns and cleanup | DataStore.java, spi/FileLocks.java | Implemented
C049 | Lifecycle | core | Partition locks | n/a | Shared lock per job; exclusive for destroy; Chronicle uses OS file locks; Ignite has none (thin client) | Never delete under a running job | spi/FileLocks.java | Implemented
C050 | Integration | core | ExecutorContext for Flink / Spark | n/a | One Spring context per executor JVM; Flink release hook; Spark lazy init | Consumers include Flink/Spark executors running Spring | spring/ExecutorContext.java | Implemented
C051 | Integration | core | Programmatic builder for tests | n/a | DataStore.builder().namespace().partition().dataset(name, class, cfg -> ...) | Unit tests without YAML | DataStore.Builder | Implemented
C052 | Testing | core | Contract tests published as test fixtures | n/a | DataStoreContractTest (22 cases) run by every store incl. custom ones | Same behaviour on all stores | testFixtures/.../DataStoreContractTest.java | Implemented
C053 | Samples | samples | Sample domain lib and Spring app | n/a | Existing-style domain (annotations + YAML-only class); pipeline create -> reference -> orders -> enrich -> export; JUnit test on memory | Requested: sample Spring consumer app | samples/** | Implemented

## YAML Reference
Key | Level | Type | Default | Allowed in dataset-defaults | Store | Description
datastore.store-type | Whole store | string | memory | No | all | memory ¦ chronicle ¦ ignite ¦ fully-qualified Store class name
datastore.namespace | Whole store | string | (required) | No | all | Owner of the data; isolates pipelines/teams sharing a host or cluster. [A-Za-z][A-Za-z0-9-]*
datastore.partition.parts | Whole store | map | (required) | No | all | Named parts joined with '_' in order → partition (e.g. NA_20261018). Each part [A-Za-z0-9-]+
datastore.lookup-resolver.parallelism | Whole store | int | 4 | No | all | Target datasets fetched in parallel per level
datastore.lookup-resolver.page-size | Whole store | int | 1000 | No | all | Page size when streaming with EAGER lookups
datastore.lookup-resolver.max-depth | Whole store | int | 0 | No | all | 0 = unlimited (full graph)
datastore.lookup-resolver.single-read-warn | Whole store | int | 10000 | No | all | Warn once per dataset after N single findById calls resolving EAGER lookups; 0 = off
datastore.extra-classes | Whole store | list | [] | No | all | Classes the codec must know that are not reachable from dataset values (e.g. subclasses)
datastore.<store> | Whole store | block | - | No | per store | Store-level settings; only the active store's block is validated
storage-mode | Dataset | enum | REFERENCE | Yes | all | REFERENCE (ids only) ¦ EMBEDDED (whole graph)
lookup-resolve-policy | Dataset | enum | LAZY | Yes | all | Default policy of this dataset's lookups: EAGER ¦ LAZY
on-missing-target | Dataset | enum | FAIL | Yes | all | When this dataset is a lookup TARGET and an id has no object: FAIL ¦ NULL
require-complete | Dataset | boolean | false | Yes | all | Refuse lookups into this dataset until its manifest status is COMPLETE
splits | Dataset | int | store default | Yes | all | Parallel scan splits (Chronicle: files; Ignite: groups of cache partitions; memory: hash groups)
local-cache | Dataset | boolean | false | Yes | all | Unbounded per-JVM ConcurrentHashMap of encoded values; for reference data
<store> | Dataset | block | - | Yes (merged per field) | per store | Dataset-level settings of the store
value | Dataset | class | (required) | No | all | Domain class stored in the dataset
key | Dataset | class | inferred | No | all | Key class; required when id lists several fields
id | Dataset | string ¦ list | @Id field | No | all | Id field, or list of fields building a composite key
lookups[].field | Lookup | path | (required) | No | all | Id field path from the value (e.g. customerId, lines.sku)
lookups[].target | Lookup | dataset | (required) | No | all | Target dataset name
lookups[].into | Lookup | field | - | No | all | Sibling field receiving the resolved object(s); required for EAGER
lookups[].name | Lookup | string | into path or field path | No | all | Name used in LookupResolver.resolve(page, name)
lookups[].lookup-resolve-policy | Lookup | enum | DEFAULT | No | all | EAGER ¦ LAZY; DEFAULT inherits dataset → dataset-defaults → LAZY

## Store Settings
Store | Level | Setting | Default | Notes
chronicle | Store | base-dir | (required) | Root: <base-dir>/<namespace>/<partition>/<dataset>/split-NNNN.cm; lock files live here
chronicle | Store | default-splits | 16 | Splits when neither dataset nor dataset-defaults sets splits
chronicle | Store | headroom | 1.2 | Capacity per split = entries × headroom ÷ splits
chronicle | Store | segments-per-split | 0 (Chronicle default) | ChronicleMapBuilder.actualSegments
chronicle | Dataset | entries | (required) | Expected total entries
chronicle | Dataset | avg-value-bytes | (required) | Average encoded value size; measure a real day
chronicle | Dataset | avg-key-bytes | computed if fixed size | Required for variable-size keys (e.g. String)
ignite | Store | addresses | (required) | Thin client addresses; one client per JVM
ignite | Store | partition-awareness | true | Send requests straight to the owning node
ignite | Store | timeout-millis | 0 | Client timeout; 0 = Ignite default
ignite | Dataset | cache-mode | PARTITIONED | PARTITIONED ¦ REPLICATED
ignite | Dataset | atomicity-mode | ATOMIC | ATOMIC ¦ TRANSACTIONAL
ignite | Dataset | backups | 1 | Ignored for REPLICATED
ignite | Dataset | data-region | - | Ignite data region name
ignite | Dataset | group-name | - | Cache group
ignite | Dataset | read-from-backup | Ignite default
ignite | Dataset | write-synchronization-mode | Ignite default | FULL_SYNC ¦ FULL_ASYNC ¦ PRIMARY_SYNC
ignite | Dataset | partition-loss-policy | Ignite default | READ_ONLY_SAFE ¦ READ_WRITE_SAFE ¦ IGNORE
ignite | Dataset | rebalance-mode | Ignite default | SYNC ¦ ASYNC ¦ NONE
ignite | Dataset | rebalance-batch-size | Ignite default
ignite | Dataset | copy-on-read | Ignite default
ignite | Dataset | statistics-enabled | Ignite default
ignite | Dataset | affinity-field | - | A component of a composite key; colocates entries with equal values
ignite | Dataset | ignite-cache-partitions | 1024 | Used to build scan splits; must match the cluster's affinity configuration
memory | Store / Dataset | (none) | - | No settings; a block for memory is an error

## Packages & Classes
Module | Package | Class | Kind | Role | Visibility
data-store-core | com.acme.datastore | DataStore | class | Entry point: builder, startup validation, DAOs, lifecycle | Public API
data-store-core | com.acme.datastore | Dao | class | Data access for one dataset: find, findAll, save, pages, streamSplit | Public API
data-store-core | com.acme.datastore | Manifest | class | Per-partition dataset status (commit point between jobs) | Public API
data-store-core | com.acme.datastore | DataStoreException | class | Unchecked library exception | Public API
data-store-core | com.acme.datastore.annotation | Id | annotation | Optional id marker | Public API
data-store-core | com.acme.datastore.annotation | Lookup | annotation | Optional lookup declaration (dataset/target, into, name, resolvePolicy) | Public API
data-store-core | com.acme.datastore.annotation | Resolve | enum | DEFAULT ¦ EAGER ¦ LAZY (config and per-call override) | Public API
data-store-core | com.acme.datastore.config | DataStoreConfig | class | YAML/JSON model incl. dataset-defaults merge and parsing | Public API
data-store-core | com.acme.datastore.lookup | LookupResolver | class | Bulk, full-depth lookup resolution engine | Public API
data-store-core | com.acme.datastore.lookup | LookupResult | class | Page-scoped lookup results / lazy scope | Public API
data-store-core | com.acme.datastore.spi | Store | interface | Storage backend SPI | SPI
data-store-core | com.acme.datastore.spi | StoreMap | interface | One dataset of one partition (bytes) | SPI
data-store-core | com.acme.datastore.spi | DatasetSpec | class | What a store knows about a dataset | SPI
data-store-core | com.acme.datastore.spi | KeyCodec | class | Deterministic key encoding, values, hash, splits | SPI
data-store-core | com.acme.datastore.spi | FileLocks | class | Cross-process partition locks (OS file locks) | SPI
data-store-core | com.acme.datastore.store | MemoryStore | class | Built-in default store (ConcurrentHashMap) | Store
data-store-core | com.acme.datastore.spring | DataStoreConfiguration | class | Plain Spring @Configuration | Public API
data-store-core | com.acme.datastore.spring | ExecutorContext | class | One Spring context per Flink/Spark executor JVM | Public API
data-store-core | com.acme.datastore.internal | Model | class | Domain model, lookup paths, strip copy, hydration | Internal (not API)
data-store-chronicle | com.acme.datastore.chronicle | ChronicleStore | class | Chronicle Map store (settings nested) | Store
data-store-ignite | com.acme.datastore.ignite | IgniteStore | class | Ignite 2 thin-client store (settings nested) | Store
sample-domain | com.acme.sample.domain | Region, Customer, Product, Order, OrderLine, Position, PositionKey | classes / record | Existing-style domain lib (compileOnly on core) | Sample
sample-app | com.acme.sample.app | AppConfig, SampleApp, Pipeline | classes | Plain Spring 7 consumer app + PipelineTest | Sample

## Tests
Suite | Test | Verifies | Memory | Custom (CountingStore) | Chronicle | Ignite
Contract (DataStoreContractTest) | roundTripAndMissingKey | Save/read one object; missing key empty; count | PASS | PASS | PASS | PASS
Contract (DataStoreContractTest) | bulkReadReturnsOnlyFoundKeys | findAllById returns only found ids | PASS | PASS | PASS | PASS
Contract (DataStoreContractTest) | readsAreCopies | Each read returns a new instance | PASS | PASS | PASS | PASS
Contract (DataStoreContractTest) | overwriteDeleteAndReset | Overwrite same id, delete, reset dataset → CREATED | PASS | PASS | PASS | PASS
Contract (DataStoreContractTest) | splitsCoverTheDatasetExactlyOnce | Splits are disjoint and cover all entries | PASS | PASS | PASS | PASS
Contract (DataStoreContractTest) | compositeRecordKeyWithEnum | Record key with enum component; scan decodes keys | PASS | PASS | PASS | PASS
Contract (DataStoreContractTest) | keyBuiltFromSeveralFields | id: [tradeId, legNo] builds a final-class key | PASS | PASS | PASS | PASS
Contract (DataStoreContractTest) | referenceModeStoresOnlyIdsAndLeavesCallerObjectsAlone | REFERENCE strips into fields, fills id from object, caller untouched | PASS | PASS | PASS | PASS
Contract (DataStoreContractTest) | referenceModeRejectsIdThatDisagreesWithObject | Id/object mismatch fails on save | PASS | PASS | PASS | PASS
Contract (DataStoreContractTest) | embeddedModeStoresTheWholeGraph | EMBEDDED keeps full graph incl. cycle; readable after target dataset reset | PASS | PASS | PASS | PASS
Contract (DataStoreContractTest) | eagerReadResolvesTheFullGraph | EAGER customer brings region and country (LAZY) — full depth | PASS | PASS | PASS | PASS
Contract (DataStoreContractTest) | cyclesTerminateAndReusePageObjects | Order → customer → primaryOrder resolves to the same object | PASS | PASS | PASS | PASS
Contract (DataStoreContractTest) | perCallOverrides | Resolve.LAZY skips; Resolve.EAGER resolves everything | PASS | PASS | PASS | PASS
Contract (DataStoreContractTest) | resolverOnDemandAndScope | scope().get loads per page; resolve(names); collection lookups | PASS | PASS | PASS | PASS
Contract (DataStoreContractTest) | streamingResolvesEagerLookupsPerPage | pages(split, size) resolves EAGER lookups | PASS | PASS | PASS | PASS
Contract (DataStoreContractTest) | missingTargetFailsByDefault | on-missing-target FAIL | PASS | PASS | PASS | PASS
Contract (DataStoreContractTest) | missingTargetIsNullWhenConfigured | on-missing-target NULL from dataset-defaults | PASS | PASS | PASS | PASS
Contract (DataStoreContractTest) | datasetOverridesDatasetDefaults | Dataset on-missing-target NULL overrides defaults FAIL | PASS | PASS | PASS | PASS
Contract (DataStoreContractTest) | manifestTracksCompletion | Manifest statuses and record counts | PASS | PASS | PASS | PASS
Contract (DataStoreContractTest) | openingBeforeCreateFails | Datasets must be created first | PASS | PASS | PASS | PASS
Contract (DataStoreContractTest) | partitionsAreIsolatedAndKeptUntilDestroyed | Partitions isolated, kept, destroyPartition, own partition protected | PASS | PASS | PASS | PASS
Contract (DataStoreContractTest) | secondStoreInSameJvmSeesTheSameData | Two DataStore instances share data | PASS | PASS | PASS | PASS
Core (DataStoreCoreTest) | eagerPageIsOneBulkCallPerDatasetPerLevel | 50 orders, EAGER: exactly one getAll per dataset, no single reads | PASS | n/a | n/a | n/a
Core (DataStoreCoreTest) | customStoreReceivesItsSettings | Custom store by class name gets its own typed settings | PASS | n/a | n/a | n/a
Core (DataStoreCoreTest) | jsonConfigWorksToo | JSON config; partition from parts | PASS | n/a | n/a | n/a
Core (DataStoreCoreTest) | validationErrors | Unknown store, blocks for Void store, unknown block, unknown target, key type mismatch, EAGER without into, no id, bad key class, ambiguous target class | PASS | n/a | n/a | n/a
Core (DataStoreCoreTest) | datasetDefaultsAreValidated | value in defaults rejected; unknown block rejected; splits inherited | PASS | n/a | n/a | n/a
Core (DataStoreCoreTest) | ambiguousClassNeedsDatasetName | Same class in two datasets needs dataset name | PASS | n/a | n/a | n/a
Core (DataStoreCoreTest) | typoInYamlIsRejectedAtStartup | datasets.country.splitz rejected | PASS | n/a | n/a | n/a
Sample (PipelineTest) | wholePipelineOnTheMemoryStore | Production YAML on memory: lookups, composite key, CSV exports | PASS | n/a | n/a | n/a

## Decisions & Open Items
Type | Topic | Status | Detail
Decision | One store per pipeline; no mixing | Agreed | store-type is a whole-store setting
Decision | namespace vs partition | Agreed | Namespace = owner (fixed); partition = run (changes every run)
Decision | Retention unlimited by default | Agreed | Delete via destroyPartition or manually
Decision | Values encoded with Fory; keys with KeyCodec | Agreed | Fory >= 1.1.0 required (CVE-2026-50076); 1.6.1 configured
Decision | Codec class registration order | Agreed | Domain classes registered sorted by name; every JVM of a partition must load the same YAML
Decision | into fields need mutable classes | Agreed | Classes on an into path in REFERENCE mode need a no-arg constructor and cannot be records (checked at startup)
Decision | Same class in two datasets | Agreed | dao(Class) fails as ambiguous; use dao("name")
Open item | Build against real libraries | Open | Sandbox could not reach Maven Central; compiled and tested against hand-written stand-ins. Run ./gradlew build with Artifactory access
Open item | API signatures to confirm | Open | Jackson 3 YAMLMapper, Fory 1.6 ThreadSafeFory, Chronicle Map builder, Ignite 2 thin client (ClientCacheConfiguration setters, ScanQuery, BinaryObjectBuilder)
Open item | Cross-JVM Chronicle sharing | Open | Stand-in keeps data in one JVM; verify multiple JVMs on real files
Open item | Live Ignite cluster | Open | ./gradlew :data-store-ignite:test -Dignite.addresses=host:10800
Open item | Chronicle Map version | Open | Central lists calendar version 2026.1; use your mirror's 3.x line if that is what it has
Risk | No distributed lock on Ignite | Accepted | destroyPartition on Ignite is not protected against jobs on other hosts; coordinate via scheduler
Risk | Unbounded local-cache | Accepted | Enable only for datasets that fit in memory
Risk | Key class changes | Mitigated | Use a new partition/namespace; Chronicle detects via key fingerprint